TERMS OF REFERENCE

| POSITION TITLE | : | Firm- Updating MPA Management Plans and Development & Piloting of Sustainable Financing for K. Togean & K. Wakatobi |
| --- | --- | --- |
| PROJECT | : | ASEAN ENMAPS – Effectively Managing Networks of Marine Protected Areas in Large Marine Ecosystems in the ASEAN Region |
| LOCATION | : | Indonesia, with project sites on K. Togean and K. Wakatobi |
| DURATION | : | Fourteen (14) months Q3 2026-Q2 2027 |
| REPORTING TO | : | National Project Manager for Indonesia, ASEAN ENMAPS |

BACKGROUND

The ASEAN ENMAPS Project supports ASEAN Member States in transitioning from site-based MPA management toward ecologically connected and effectively governed MPA networks. In Indonesia, Kepulauan Togean and Kepulauan Wakatobi National Parks are priority sites where biodiversity conservation, fisheries sustainability, and community livelihoods intersect within complex governance and socio-economic contexts.

Existing MPA management plans in these sites provide a foundation for conservation but require updating to reflect recent scientific findings, including resource assessments, connectivity analyses, and socio-economic and governance studies. In addition, SESA results and METT assessments highlight the need for improved governance arrangements, stakeholder participation, and enforcement mechanisms. Stakeholder engagement is critical to ensure that management strategies are grounded in local realities, incorporate traditional knowledge, and address the needs of coastal communities, including women, indigenous peoples, and resource-dependent sectors.

At the same time, the sustainability of MPA management remains constrained by limited and uncertain financing. There is a need to identify and operationalize sustainable financing mechanisms that can support conservation actions, strengthen institutional capacity, and deliver socio-economic benefits. Integrating stakeholder engagement with financing development ensures that proposed mechanisms are feasible, socially accepted, and aligned with governance structures.

This consultancy adopts an integrated approach to bridge planning and implementation by combining consultations, management plan enhancement, sustainable financing development, and pilot implementation within a single process, with dedicated MPA management plan updating write-shops to be conducted in Kepulauan Togean and Kepulauan Wakatobi National Parks to ensure direct translation of stakeholder inputs into implementable management plan provisions.

SCOPE OF WORK

- Review of Existing MPA Management Plans and Financing Structures

The consultancy will conduct a comprehensive review of existing MPA management plans, including objectives, zoning schemes, resource use regulations, and governance arrangements, to identify gaps and areas for improvement based on recent scientific assessments, including SESA and METT results. In parallel, the consultancy will review and analyze existing financing mechanisms, policies, and institutional arrangements supporting MPA management to identify viable and sustainable financing options, drawing on relevant case studies and best practices from Indonesia, the ASEAN region, and global experiences, ensuring alignment with UNDP Social and Environmental Standards.

- Design of Consultation Framework

In close coordination with National Parks, the Gender and Safeguards Specialist, FPIC facilitators, and other relevant partners, the consultancy will design a participatory consultation framework and engagement plan. This framework will ensure inclusive and equitable participation of diverse stakeholder groups, including government agencies, coastal communities, women, youth, masyarakat adat, fisherfolk organizations, and private sector actors.

- Conduct of Multi-Stakeholder Consultations

The consultancy will facilitate multi-stakeholder consultations through workshops, focus group discussions (FGDs), key informant interviews (KIIs), SWOT analysis, and other appropriate participatory approaches. These consultations will generate qualitative and quantitative inputs on management priorities, governance challenges, resource use, and potential financing mechanisms, The process will ensure that stakeholder perspectives directly inform the enhancement of management plans and the design of financing strategies, with a target of engaging at least 80 stakeholders.

- Validation and Stakeholder Alignment

The consultancy will present draft management and financing outputs to stakeholders for validation. Feedback will be documented and incorporated to ensure that outputs are technically sound, socially acceptable, and institutionally feasible.

- Consolidation of Stakeholder Feedback and Development of Recommendations

The consultancy will synthesize consultation outputs into a structured set of findings, highlighting key themes, emerging issues, and consensus recommendations. These will include actionable proposals to improve MPA management effectiveness, governance inclusivity, resource sustainability, and community benefit-sharing mechanisms, ensuring alignment with gender-responsive and safeguards-based approaches.

- Development of Business and Sustainable Financing Plans

Based on the results of the consultations and agreed management directions, the consultancy will develop site-specific business and sustainable financing plans. These plans shall outline operational, financial, and institutional strategies, including projected revenue streams, cost structures, investment requirements, risk assessments, implementation timelines, and monitoring frameworks, demonstrating how financing mechanisms will support biodiversity conservation objectives and socio-economic benefits for local communities.

- Conduct of MPA Management Plan Updating Write-Shops

The consultancy will organise and facilitate dedicated write-shops for updating MPA management plans─one in Kepulauan Togean National Park and one in Kepulauan Wakatobi National Park. A technical working draft report, structured into modular, insert-ready sections aligned with MPA management plan components (e.g., governance, zoning, MCS, financing, livelihoods), shall be prepared and made available in advance and during the write-shops to guide deliberations. These write-shops will enable stakeholders to directly translate validated consultation outputs, agreed strategies, and pilot implementation learnings into draft, site-specific management plan provisions that are immediately usable for plan updating.

.

- Pilot Implementation of Financing Strategies

The consultancy will identify and recommend the most feasible financing mechanism(s) for pilot implementation and support initial operationalization. This will include facilitating stakeholder commitments, clarifying institutional roles, and establishing practical arrangements for implementation beyond the project period.

- Integrated Analysis and Final Report

The consultancy will produce a comprehensive final report that consolidates all outputs of the assignment, including technical analyses, stakeholder consultation results, validated recommendations, sustainable financing strategies, and pilot implementation outcomes. The report shall include as annexes or embedded sections the updated management plan components for Kepulauan Togean and Kepulauan Wakatobi, integrating financing strategies and reflecting pilot implementation experience. The final report will also document lessons learned, implementation guidance, and recommendations to support decision-making and scaling at site and national levels..

EXPECTED OUTPUTS/DELIVERABLES

The Consultancy Firm is expected to provide the following deliverables. Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Deliverables | Description | Date of Submission |
| --- | --- | --- |
| Inception Report Project schedule and workplan | Approved project schedule, consultation design framework and workplan | 2-4 weeks after contract signing |
| Output 1 Review of Existing MPA Management Plans and Financing Structures; Design of Consultation Framework | Report on the review of the MPA Management plans of K. Togean NP and Wakatobi NP; Design of Consultation framework and plan submitted for approval of the NPs | Month 3 |
| Output 2 Consolidation of Stakeholder Feedback and Development of Recommendations Development of Business and Sustainable Financing Plans | Report of multistakeholder consultations, results of validation meetings, including documentation of participants, disaggregated by gender; FPIC documentation where applicable; key agreements and recommendations; Draft Business/ Sustainable Financing Plans (2) submitted to the national parks for approval | Month 5 |
|  | Approved recommendations for Sustainable Financing to guide revenue generation for K. Togean and Wakatobi NP |  |
| Output 3 Conduct of MPA Management Plan Updating Write-Shops | Report on the results of convening of the dedicated MPA management plan updating writeshops; including documentation of participants, disaggregated by gender, draft updated MPA plans submitted to the National Parks | Month 7 |
| Output 4 Pilot Implementation of Financing Strategies Pilot Implementation Plan | Implementation plan outlining activities, schedules, and expected outputs |  |
| 4a. Periodic Report | Progress report 3 months following mobilisation of pilot implementation | Month 10 |
| 4b. Periodic Report | Progress report 3 months following pilot implementation | Month 13 |
| Output 5 Integrated Analysis and Final Report | Consolidated outputs, including technical analyses, stakeholder consultation results, validated recommendations, sustainable financing strategies, and pilot implementation outcomes | Month 14 |

DURATION AND TIMELINE

The consultancy is expected to run for fourteen (14) months, starting from the date of the contract signing.

QUALIFICATIONS REQUIREMENT

Required:

- Indonesia-registered firm/institution with authorisation to work within Indonesia

- Presence in K. Togean and K. Wakatobi or adjacent communities is highly preferred

- Demonstrated expertise in environmental governance or policy, sustainable or conservation financing, resource economics, resource management, or conservation/biodiversity-related fields

- Prior experience working with MPAs and National Parks in Indonesia

- Adequate understanding of Indonesia’s coastal and marine governance structures, including decentralisation frameworks

- Experience in developing business plans, feasibility studies, or investment proposals

- Success in implementing/managing conservation-related business is an advantage

- Ability to work independently and collaboratively, manage multiple priorities under tight deadlines, and deliver high-quality outputs in complex and dynamic environments

- Proficiency in English, to facilitate communication with the National Project Manager and other project staff and consultants

- Familiarity with ASEAN regional frameworks, the role of the ASEAN Centre for Biodiversity (ACB), and relevant multilateral environmental agreements is an advantage

IMPLEMENTATION ARRANGEMENT

The Consultancy Firm shall coordinate with the ASEAN ENMAPS National Project Manager, the Ministry of Forestry as  assigned National Focal Agency coordinator, National Parks  and with relevant Site Officers as necessary.

Periodic project reports are to be submitted for review to the ASEAN ENMAPS National Project Manager and the assigned National Focal Agency coordinator

All reports will be approved by the Project Management Unit-ACB upon endorsement of the National Project Manager.